## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | User Interface | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Frontend Developer | 2025-12-07 | Loan form submit button not sending data to backend API. | Sprint 1 | Backend Developer | User Interface | Fixed incorrect API route and enabled CORS. | 2025-12-08 | Closed | Form submission works properly.
2 | AI/ML Engineer | 2025-12-09 | AI model returning prediction but no explanation values (SHAP output empty). | Sprint 1 | ML Engineer | Logical | Corrected data preprocessing and SHAP initialization. | 2025-12-10 | Closed | Explanations generated correctly.
3 | AI/ML Engineer | 2025-12-11 | some features(like home ownership) are too much shaping final prediction | Sprint 2 | ML Engineer | Logical | Added Regularisation to model building | 2025-12-12 | Closed | All features have fair share in prediction
4 | Backend Engineer | 2025-12-13 | loan percentage feature not auto calculating | Sprint 2 | Backend Developer | Maintainability | corrected semantic and mathematical bugs | 2025-12-14 | Closed | Dashboard reflects correct status.
5 | Chatbot Developer | 2025-12-15 | Chatbot not responding to eligibility-related questions. | Sprint 2 | NLP Engineer | Standards | Improved intent matching and added training phrases. | 2025-12-16 | Closed | Chatbot responds accurately.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others